## Sheet1
Project | MA Workflow Optimization
Issue | Severity | Impact | Resolution Item | Status | Owner
Feedback delay from providers | High | Extended timeline by 2 weeks | Sent reminders, adjusted milestones | Closed | Project Lead
Short-staff during pilot phase | Medium | Reduced testing window | Adjusted pilot dates and included float staff | Closed | Project Lead
Inconsistent adoption of workflow | Medium | Break in process flow | Conducted retraining for MAs | Closed | Project Lead