## Sheet1
Project: | MA Workflow Optimization
Risk | Likelihood | Impact | Mitigation Strategy | Owner
Delayed Provider Feedb | High | High | Send early requests, include deadlines and reminders | Project Lead
Staff Shortages | Medium | High | Use phased implementation, assign backups | Project Lead
Resistance to Change | Medium | Medium | Conduct early engagement and include MAs in proce | Project Lead
Data Inconsistency | Low | Medium | Use standardized templates and training checks | Project Lead
Timeline Creep | Medium | High | Use Gantt milestones and weekly status updates | Project Lead